# DataTrial EDC/IWRS System

# Project Cost Estimate - Fast Track Delivery

Document Version: 1.0 Date: January 28, 2026 Currency: INR (Indian Rupees) Validity: 30 Days Budget: ₹1,20,00,000 (One Crore Twenty Lakhs) Delivery Model: Accelerated / Fast Track

## 1. Executive Summary

| Item | Details |
| --- | --- |
| Project | Enterprise EDC/IWRS Clinical Trial Management System |
| Technology | Next.js + Supabase (PostgreSQL) |
| Compliance | US FDA 21 CFR Part 11, ICH-GCP |
| Timeline | 3-4 Months (16 Weeks) |
| Team Size | 12-15 Members (3 Parallel Squads) |
| Delivery Model | Agile Sprints with Parallel Development |
| Total Investment | ₹1,20,00,000 |

## 2. Fast Track Delivery Approach

### 2.1 Parallel Development Strategy

┌─────────────────────────────────────────────────────────────────────────────┐
│                        WEEK 1-2: SPRINT 0 (Foundation)                       │
│         Architecture Setup | Design System | Database Schema | Auth          │
└─────────────────────────────────────────────────────────────────────────────┘
                                      │
        ┌─────────────────────────────┼─────────────────────────────┐
        ▼                             ▼                             ▼
┌───────────────────┐    ┌───────────────────┐    ┌───────────────────┐
│     SQUAD A       │    │     SQUAD B       │    │     SQUAD C       │
│   (2-3 Members)   │    │   (2-3 Members)   │    │   (2-3 Members)   │
├───────────────────┤    ├───────────────────┤    ├───────────────────┤
│ • Study Setup     │    │ • CRF Builder     │    │ • IWRS Module     │
│ • User Management │    │ • Data Entry      │    │ • IP Management   │
│ • Site Management │    │ • Query Mgmt      │    │ • Randomization   │
│ • Audit Trail     │    │ • Workflows       │    │ • Shipments       │
│ • Reports         │    │ • Data Lock       │    │ • Dispensing      │
└───────────────────┘    └───────────────────┘    └───────────────────┘
        │                             │                             │
        └─────────────────────────────┼─────────────────────────────┘
                                      ▼
┌─────────────────────────────────────────────────────────────────────────────┐
│                    WEEK 13-16: Integration | UAT | Go-Live                   │
└─────────────────────────────────────────────────────────────────────────────┘

### 2.2 Sprint Timeline (16 Weeks)

| Sprint | Weeks | Squad A | Squad B | Squad C |
| --- | --- | --- | --- | --- |
| Sprint 0 | 1-2 | Architecture, Auth, DB Setup | UI Design System | Infrastructure Setup |
| Sprint 1 | 3-4 | User & Role Management | Form Designer | Kit Definition |
| Sprint 2 | 5-6 | Study & Site Setup | Field Types & Validations | IP Inventory |
| Sprint 3 | 7-8 | Audit Trail & e-Sign | Subject Management | Randomization Engine |
| Sprint 4 | 9-10 | Dashboard & Reports | CRF Data Entry | Shipment Management |
| Sprint 5 | 11-12 | Data Export & Reports | Query Management | Kit Dispensing |
| Sprint 6 | 13-14 | Integration Testing | Workflow & Review | Integration Testing |
| Sprint 7 | 15-16 | UAT & Bug Fixes | UAT & Bug Fixes | Go-Live Support |

## 3. Cost Summary

| Category | Amount (₹) |
| --- | --- |
| Squad A - Core Platform & Admin | 32,90,000 |
| Squad B - EDC Module | 40,60,000 |
| Squad C - IWRS Module | 26,60,000 |
| UI/UX Design Team | 9,57,000 |
| Quality Assurance Team | 10,98,000 |
| Validation & Compliance | 6,00,000 |
| Infrastructure & DevOps (Year 1) | 6,00,000 |
| Project Management | 9,35,000 |
| Subtotal | ₹1,42,00,000 |
| Fast Track Discount (15.5%) | (₹22,00,000) |
| Final Project Cost | ₹1,20,00,000 |

## 4. Payment Schedule (Milestone-Based)

| Milestone | Week | Deliverables | % | Amount (₹) |
| --- | --- | --- | --- | --- |
| M0 | 0 | Contract Signing | 20% | 24,00,000 |
| M1 | 2 | Sprint 0: Architecture, Design System, DB Ready | 15% | 18,00,000 |
| M2 | 6 | Core Platform, User Mgmt, CRF Builder Basic | 20% | 24,00,000 |
| M3 | 10 | EDC Complete, IWRS Basic, Reports | 20% | 24,00,000 |
| M4 | 14 | Full Integration, UAT Ready | 15% | 18,00,000 |
| M5 | 16 | Go-Live, Handover | 10% | 12,00,000 |
|  |  | Total | 100% | ₹1,20,00,000 |

## 5. Team Composition (12-15 Members)

| Role | Count | Duration | Responsibility |
| --- | --- | --- | --- |
| Project Manager | 1 | 16 weeks | Overall delivery, Client coordination |
| Technical Architect | 1 | 16 weeks | Architecture, Technical decisions |
| Tech Lead / Scrum Master | 1 | 16 weeks | Agile process, Technical oversight |
| Squad A Developers | 2-3 | 16 weeks | Core platform, Admin, Reports |
| Squad B Developers | 2-3 | 16 weeks | EDC, CRF Builder, Data Entry |
| Squad C Developers | 2-3 | 16 weeks | IWRS, Randomization, Shipments |
| UI/UX Designer | 1 | 12 weeks | Design system, All screens |
| QA Engineers | 2 | 14 weeks | Testing, Automation |
| DevOps Engineer | 1 | 16 weeks | Infrastructure, CI/CD |
| Total | 14-16 |  |  |

## 6. Delivery Commitment & SLAs

| Metric | Commitment |
| --- | --- |
| Go-Live Date | Week 16 from Kickoff |
| Core Modules Delivery | Week 10 (UAT Ready) |
| Critical Bug Resolution | 24 hours |
| Sprint Delivery | Every 2 weeks |
| Daily Standups | Yes (with client optional) |
| Weekly Demo | Every Friday |
| Warranty Period | 90 days post Go-Live |

## 7. Terms, Assumptions & Exclusions

Terms: - Validity: 30 days | Taxes: GST 18% extra | Payment: Net 7 days

Assumptions: - Requirements frozen after Sprint 0 - Client decisions within 24-48 hours - Dedicated client SPOC available - Cloud deployment only (Supabase) - English language (single) - Up to 100 concurrent users - Client to handle end-user training internally

Exclusions: - MedDRA/WHODrug licenses - On-premise deployment - Multi-language support - Native mobile apps - Third-party audits - Training programs (Train-the-trainer / End-user) - Scope changes post Sprint 0

## 8. Risk Mitigation for Fast Track

| Risk | Mitigation |
| --- | --- |
| Requirement changes | Frozen scope after Sprint 0, CR process |
| Resource availability | Backup resources identified, Cross-training |
| Integration delays | Early integration testing from Sprint 4 |
| Quality compromise | Dedicated QA team, Automated testing |
| Timeline slip | Daily monitoring, Buffer in Sprint 6-7 |

Prepared By: DataTrial Solutions Delivery Commitment: 16 Weeks from Contract Signing Contact: [Your Contact Information]

Fast track delivery requires committed collaboration from both teams. Timeline is achievable with scope freeze and quick decisions.