## Master Launch Plan
PHYSIOCONNECT — COMPLETE LAUNCH PLAN
🚀 Launch: 30 March 2026 ¦ UK Home Physiotherapy Marketplace ¦ Today: 2 March 2026 ¦ 28 Days to Launch
🔵 SRH = Operations Team (UK) — Legal, Compliance, Recruitment, Marketing, Finance, Content, Ops ¦ 🟣 RCB = Technical Team (Bangalore) — Dev, Infra, Payments, QA, Design
# | Date | Day | Category | Task | Details / Notes | Owner | Priority | Status | Dependencies
1 | 02 Mar 2026 | Mon | Legal & Company Formation | Register company with Companies House | Register Ltd company online (24hr turnaround). Cost: £12. Use web filing service | SRH | CRITICAL | Not Started
2 | 02 Mar 2026 | Mon | Legal & Company Formation | Choose company name & check availability | Search Companies House register + domain availability. Finalise name | SRH | CRITICAL | Not Started
3 | 02 Mar 2026 | Mon | Legal & Company Formation | Register domain name (.co.uk + .com) | Namecheap / GoDaddy. Cost ~£10-20. Secure both extensions immediately | SRH | CRITICAL | Not Started
4 | 02 Mar 2026 | Mon | Legal & Company Formation | Appoint directors & shareholders | Form IN01. Decide share structure. Registered office address needed | SRH | HIGH | Not Started | Company name
5 | 02 Mar 2026 | Mon | Finance & Banking | Apply for business bank account | Tide / Starling / Monzo Business (fastest approval). Need: Co. number, ID, proof of address | SRH | CRITICAL | Not Started | Company reg
6 | 02 Mar 2026 | Mon | Regulatory & Compliance | Research HCPC registration requirements | All physios must be HCPC registered. Understand verification process for platform | SRH | CRITICAL | Not Started
7 | 02 Mar 2026 | Mon | Regulatory & Compliance | Research CSP membership verification | Chartered Society of Physiotherapy. Adds credibility. Plan how to verify | SRH | HIGH | Not Started
8 | 02 Mar 2026 | Mon | Technical - Infrastructure | Set up GitHub repository & branching | Create repo, main/develop branches, .gitignore, README, CI basics | RCB | CRITICAL | Not Started
9 | 02 Mar 2026 | Mon | Technical - Infrastructure | Set up development environment | Next.js project (exists). Verify Node, install deps, lint config, env vars | RCB | CRITICAL | Not Started
10 | 02 Mar 2026 | Mon | Design & Branding | Design logo and brand identity | Colours, typography, brand guidelines. Fiverr/99designs for fast turnaround | RCB | HIGH | Not Started
11 | 03 Mar 2026 | Tue | Legal & Company Formation | Draft Terms of Service | Platform terms, booking terms, cancellation policy, liability. Template + solicitor review | SRH | CRITICAL | Not Started
12 | 03 Mar 2026 | Tue | Legal & Company Formation | Draft Privacy Policy (UK GDPR) | UK GDPR & Data Protection Act 2018. Data collected, processing, retention, rights | SRH | CRITICAL | Not Started
13 | 03 Mar 2026 | Tue | Legal & Company Formation | Register with ICO | Data protection registration. £35-40/yr. Legal requirement for personal data processing | SRH | CRITICAL | Not Started | Company reg
14 | 03 Mar 2026 | Tue | Insurance | Research & obtain Public Liability Insurance | Platform-level PLI. Hiscox / Simply Business / AXA. Require physios to have own PLI | SRH | CRITICAL | Not Started | Company reg
15 | 03 Mar 2026 | Tue | Insurance | Research Professional Indemnity Insurance | PI insurance for platform operations. Physios must have own PI via practice | SRH | HIGH | Not Started
16 | 03 Mar 2026 | Tue | Technical - Infrastructure | Set up cloud hosting (Vercel) | Deploy Next.js to Vercel. Set up staging + production environments | RCB | CRITICAL | Not Started | GitHub repo
17 | 03 Mar 2026 | Tue | Technical - Infrastructure | Set up database (Supabase/PostgreSQL) | Supabase (Postgres + Auth + Realtime). Tables, RLS policies. Free tier | RCB | CRITICAL | Not Started
18 | 03 Mar 2026 | Tue | Technical - Backend | Design complete database schema | Tables: users, physios, bookings, reviews, availability, payments, addresses, qualifications, services | RCB | CRITICAL | Not Started
19 | 03 Mar 2026 | Tue | Technical - Backend | Set up authentication system | Supabase Auth or NextAuth.js. Email/password + Google OAuth. Separate patient & physio flows | RCB | CRITICAL | Not Started | DB setup
20 | 04 Mar 2026 | Wed | 💰 Payment: SRH → RCB | SRH pays ₹50,000 (1st instalment) to RCB | 1st of 3 instalments. Total ₹1,50,000. Bank transfer/UPI to RCB. Collect receipt immediately | SRH | CRITICAL | Not Started | Bank account
21 | 04 Mar 2026 | Wed | Legal & Company Formation | Register for HMRC / Corporation Tax | Register within 3 months. Get UTR number. Consider VAT threshold (£90k) | SRH | HIGH | Not Started | Company reg
22 | 04 Mar 2026 | Wed | Legal & Company Formation | Draft Physiotherapist Agreement / Contract | Independent contractor agreement. Commission, standards, cancellation, insurance, HCPC | SRH | CRITICAL | Not Started
23 | 04 Mar 2026 | Wed | Technical - Backend | Build physio registration & onboarding flow | Multi-step: personal details, qualifications, HCPC no., services, areas, availability | RCB | CRITICAL | Not Started | Auth system
24 | 04 Mar 2026 | Wed | Technical - Backend | Build HCPC verification integration | HCPC online register - scraper/API to verify physio status. Critical for trust & safety | RCB | CRITICAL | Not Started
25 | 04 Mar 2026 | Wed | Technical - Frontend | Build landing page / homepage | Hero, how it works, benefits, trust signals, CTAs. Mobile-first design | RCB | CRITICAL | Not Started | Design ready
26 | 04 Mar 2026 | Wed | Content & Copywriting | Write website copy — Homepage | Value proposition, how it works steps, patient benefits, trust messaging | SRH | HIGH | Not Started
27 | 04 Mar 2026 | Wed | Physio Recruitment | Create physio recruitment campaign plan | Channels: LinkedIn, CSP jobs board, FB groups, Indeed, local networks | SRH | CRITICAL | Not Started
28 | 05 Mar 2026 | Thu | 💰 Payment: SRH → RCB | SRH pays ₹50,000 (2nd instalment) to RCB | 2nd instalment. Running total: ₹1,00,000 / ₹1,50,000. Bank transfer. Get receipt | SRH | CRITICAL | Not Started | 1st paid
29 | 05 Mar 2026 | Thu | Technical - Frontend | Build patient registration flow | Sign-up: name, email, phone, postcode, medical conditions (optional) | RCB | HIGH | Not Started | Auth system
30 | 05 Mar 2026 | Thu | Technical - Backend | Build physio profile & dashboard | Profile: bio, qualifications, specialisms, reviews, availability calendar, earnings | RCB | CRITICAL | Not Started | Physio reg
31 | 05 Mar 2026 | Thu | Technical - Backend | Build service listing & search engine | Services list (sports, rehab, elderly). Search by postcode + service type | RCB | CRITICAL | Not Started | DB schema
32 | 05 Mar 2026 | Thu | Technical - Backend | Build availability management system | Weekly availability, calendar view, block dates, recurring schedules | RCB | HIGH | Not Started | Physio dashboard
33 | 05 Mar 2026 | Thu | Physio Recruitment | Post job listings on all channels | LinkedIn, Indeed, CSP job board, Gumtree, physio FB groups, Reed.co.uk | SRH | CRITICAL | Not Started | Recruitment plan
34 | 05 Mar 2026 | Thu | Physio Recruitment | Direct outreach to local physios | Find private physios in target area. Personal email/LinkedIn with value prop | SRH | HIGH | Not Started
35 | 05 Mar 2026 | Thu | Content & Copywriting | Write copy — About page, How it Works | Detailed how-it-works for patients & physios. FAQ content drafts | SRH | HIGH | Not Started
36 | 06 Mar 2026 | Fri | 💰 Payment: SRH → RCB | SRH pays ₹50,000 (3rd / FINAL instalment) | FINAL instalment. ₹1,50,000 FULLY PAID. Get final receipt. Confirm settlement in writing | SRH | CRITICAL | Not Started | 2nd paid
37 | 06 Mar 2026 | Fri | Technical - Frontend | Build physio search results page | Cards: photo, name, specialisms, rating, distance, price, next available. Filters & sort | RCB | CRITICAL | Not Started | Search backend
38 | 06 Mar 2026 | Fri | Technical - Frontend | Build physio public profile page | Full profile: about, qualifications, reviews, services & prices, book-now CTA | RCB | HIGH | Not Started | Profile backend
39 | 06 Mar 2026 | Fri | Technical - Payments | Set up Stripe Connect account | Apply for UK Stripe Connect. Marketplace model. Connected accounts for physios | SRH | CRITICAL | Not Started | Company + Bank
40 | 06 Mar 2026 | Fri | Marketing & Pre-Launch | Set up all social media accounts | Instagram, Facebook Page, LinkedIn Company, Twitter/X. Consistent branding | SRH | HIGH | Not Started | Logo ready
41 | 06 Mar 2026 | Fri | Design & Branding | Design social media templates | Post templates, story templates, brand-consistent look. Canva / Figma | RCB | MEDIUM | Not Started | Branding
42 | 07 Mar 2026 | Sat | Technical - Payments | Build payment flow (Stripe integration) | Patient pays → Stripe holds → appointment done → release to physio minus commission | RCB | CRITICAL | Not Started | Stripe account
43 | 07 Mar 2026 | Sat | Technical - Backend | Build booking system | Select service → date/time → address → confirm → pay → confirmation emails | RCB | CRITICAL | Not Started | Availability + Payments
44 | 07 Mar 2026 | Sat | Technical - Backend | Build email notification system | Booking confirm, 24hr reminders, cancellation notices, welcome. SendGrid / Resend | RCB | HIGH | Not Started
45 | 07 Mar 2026 | Sat | Marketing & Pre-Launch | Create Google My Business listing | GMB for local SEO. Business details, photos, services | SRH | MEDIUM | Not Started | Company reg
46 | 08 Mar 2026 | Sun | Technical - Backend | Build booking management — physio side | Upcoming bookings, accept/decline, patient details, navigate to address, mark complete | RCB | CRITICAL | Not Started | Booking system
47 | 08 Mar 2026 | Sun | Technical - Backend | Build booking management — patient side | View bookings, upcoming & past, cancel/reschedule, leave review | RCB | HIGH | Not Started | Booking system
48 | 08 Mar 2026 | Sun | Technical - Frontend | Build booking flow UI (wizard) | Step-by-step booking wizard. Mobile-responsive. Clean, reassuring design | RCB | CRITICAL | Not Started | Booking backend
49 | 08 Mar 2026 | Sun | Content & Copywriting | Write physio onboarding guide | Step-by-step: set up profile, manage bookings, get paid, support contacts | SRH | HIGH | Not Started
50 | 09 Mar 2026 | Mon | Technical - Backend | Build review & rating system | Patient rates physio (1-5 stars) + written review. Physio can respond | RCB | HIGH | Not Started | Booking complete
51 | 09 Mar 2026 | Mon | Technical - Backend | Build admin dashboard | All bookings, users, physios, revenue, disputes, pending verifications. KPIs | RCB | HIGH | Not Started
52 | 09 Mar 2026 | Mon | Technical - Frontend | Build patient dashboard | My bookings, upcoming, past treatments, saved physios, profile settings | RCB | HIGH | Not Started | Booking mgmt
53 | 09 Mar 2026 | Mon | Physio Recruitment | Follow up with interested physios | Respond to applications, onboarding calls, answer commission / platform questions | SRH | CRITICAL | Not Started | Listings posted
54 | 09 Mar 2026 | Mon | Legal & Company Formation | Finalise platform commission structure | Decide commission rate (15-25%). Clear pricing model for physio agreement | SRH | CRITICAL | Not Started
55 | 10 Mar 2026 | Tue | Technical - Backend | Build cancellation & refund system | 24hr free cancel. Late cancel fee 50%. No-show handling. Auto Stripe refunds | RCB | CRITICAL | Not Started | Payment system
56 | 10 Mar 2026 | Tue | Technical - Backend | Build postcode / location matching | postcodes.io (free UK API). Distance calc. Match physios within X miles | RCB | CRITICAL | Not Started
57 | 10 Mar 2026 | Tue | Technical - Backend | Build SMS notifications (Twilio) | Booking confirms & reminders via SMS. UK mobiles. Optional at launch | RCB | MEDIUM | Not Started
58 | 10 Mar 2026 | Tue | Physio Recruitment | Onboard first physios onto platform | Help create profiles, upload docs, set availability, verify HCPC | SRH | CRITICAL | Not Started | Physio reg flow
59 | 10 Mar 2026 | Tue | Operations & Support | Set up customer support email | support@domain. Shared inbox: Zendesk free / Freshdesk / Gmail | SRH | HIGH | Not Started | Domain
60 | 11 Mar 2026 | Wed | Technical - Frontend | Mobile responsiveness pass — all pages | Test & fix every page on mobile. iPhone & Android. Most bookings from mobile | RCB | CRITICAL | Not Started | All frontend
61 | 11 Mar 2026 | Wed | Technical - Backend | Build in-app messaging system | Secure messaging patient ↔ physio. Pre-appointment Qs. No phone sharing | RCB | HIGH | Not Started
62 | 11 Mar 2026 | Wed | Technical - Backend | Implement DBS check verification workflow | Enhanced DBS for home visits. Upload & admin verification flow | RCB | HIGH | Not Started
63 | 11 Mar 2026 | Wed | Regulatory & Compliance | Create safeguarding policy | Safeguarding vulnerable adults. Required for home healthcare. DBS reqs | SRH | CRITICAL | Not Started
64 | 11 Mar 2026 | Wed | Regulatory & Compliance | Create complaints procedure | Formal complaints handling. Align with HCPC standards. Escalation path | SRH | HIGH | Not Started
65 | 11 Mar 2026 | Wed | Content & Copywriting | Write FAQ page content | How it works, pricing, insurance, qualifications, cancellation, safety | SRH | HIGH | Not Started
66 | 12 Mar 2026 | Thu | Technical - Backend | Build automated email sequences | Welcome series, post-booking follow-up, review request (24hr), re-engagement | RCB | HIGH | Not Started | Email system
67 | 12 Mar 2026 | Thu | Marketing & Pre-Launch | Set up Google Analytics & tracking | GA4, Meta Pixel, conversion tracking. Track: sign-ups, bookings, revenue | RCB | HIGH | Not Started
68 | 12 Mar 2026 | Thu | Marketing & Pre-Launch | Create pre-launch landing page with waitlist | Coming-soon page + email capture. Value prop, launch date countdown | RCB | HIGH | Not Started
69 | 12 Mar 2026 | Thu | Physio Recruitment | Continue onboarding — target 10-15 physios | Minimum viable supply. Focus 2-3 London boroughs or target city | SRH | CRITICAL | Not Started
70 | 12 Mar 2026 | Thu | Insurance | Finalise & purchase all insurance policies | PLI + PI purchased. Certificates saved. Renewal dates diarised | SRH | HIGH | Not Started | Insurance research
71 | 13 Mar 2026 | Fri | Technical - Testing & QA | Full E2E testing — Patient journey | Sign up → search → profile → book → pay → confirm → cancel → refund | RCB | CRITICAL | Not Started | All features
72 | 13 Mar 2026 | Fri | Technical - Testing & QA | Full E2E testing — Physio journey | Register → verify → availability → booking → navigate → complete → paid | RCB | CRITICAL | Not Started | All features
73 | 13 Mar 2026 | Fri | Technical - Testing & QA | Payment testing (Stripe test mode) | All scenarios: success, failed card, refund, physio payout, partial | RCB | CRITICAL | Not Started | Payments
74 | 13 Mar 2026 | Fri | Technical - Testing & QA | Basic security audit | Auth flows, SQL injection, XSS, CSRF, rate limiting. OWASP top 10 | RCB | CRITICAL | Not Started
75 | 13 Mar 2026 | Fri | Marketing & Pre-Launch | Create launch marketing materials | Social posts (2 weeks), email announcement, press release draft | SRH | HIGH | Not Started | Branding
76 | 13 Mar 2026 | Fri | Marketing & Pre-Launch | Set up email marketing (Mailchimp/Brevo) | Account, import waitlist, welcome email series, booking reminders | SRH | HIGH | Not Started
77 | 14 Mar 2026 | Sat | Technical - Testing & QA | Fix all bugs from E2E testing | Address every critical & high bug found. Regression test after fixes | RCB | CRITICAL | Not Started | E2E testing
78 | 14 Mar 2026 | Sat | Technical - Infrastructure | Set up error monitoring (Sentry) | Frontend & backend error tracking. Slack/email alerts for critical failures | RCB | HIGH | Not Started
79 | 14 Mar 2026 | Sat | Content & Copywriting | Write blog posts for launch | 2-3 SEO articles: 'Benefits of home physio', 'How to choose a physio' | SRH | MEDIUM | Not Started
80 | 14 Mar 2026 | Sat | Operations & Support | Create support documentation / help centre | How to book, payment Qs, cancellation, physio FAQ, patient FAQ | SRH | HIGH | Not Started
81 | 15 Mar 2026 | Sun | Technical - Frontend | Performance optimisation | Lighthouse audit. Image opt, lazy loading, code splitting. Target 90+ | RCB | HIGH | Not Started
82 | 15 Mar 2026 | Sun | Technical - Frontend | SEO setup | Meta tags, OG, Schema.org LocalBusiness, sitemap.xml, robots.txt | RCB | HIGH | Not Started
83 | 15 Mar 2026 | Sun | Operations & Support | Create internal operations playbook | Disputes, refunds, complaints, emergencies, escalation procedures | SRH | HIGH | Not Started
84 | 16 Mar 2026 | Mon | Technical - Infrastructure | Set up custom domain & SSL | Point domain → Vercel. SSL auto. www redirect. Email forwarding | RCB | CRITICAL | Not Started | Domain + Hosting
85 | 16 Mar 2026 | Mon | Technical - Infrastructure | Set up production database & backups | Production Supabase. Automated daily backups. DR plan documented | RCB | CRITICAL | Not Started
86 | 16 Mar 2026 | Mon | Technical - Infrastructure | Set up CDN & image hosting | Cloudflare / Vercel Edge. Cloudinary or S3 for photos & docs | RCB | HIGH | Not Started
87 | 16 Mar 2026 | Mon | Technical - Payments | Switch Stripe to live mode | Activate live. Verify bank connected. Real £1 test. Webhook endpoints | RCB | CRITICAL | Not Started | Stripe test pass
88 | 16 Mar 2026 | Mon | Physio Recruitment | Verify all onboarded physios | HCPC ✓, insurance docs ✓, DBS ✓, profile complete ✓, bank for payout ✓ | SRH | CRITICAL | Not Started | Onboarding
89 | 16 Mar 2026 | Mon | Marketing & Pre-Launch | Set up Google Ads account (prep) | Account, conversion tracking, draft campaign. Postcode + physio keywords | SRH | MEDIUM | Not Started
90 | 17 Mar 2026 | Tue | Technical - Testing & QA | Staging environment full test | Deploy to staging. Complete walkthrough all flows. Test with real physio accounts | RCB | CRITICAL | Not Started | All dev done
91 | 17 Mar 2026 | Tue | Technical - Testing & QA | Cross-browser testing | Chrome, Safari, Firefox, Edge. Mobile Safari (iPhone), Chrome (Android) | RCB | HIGH | Not Started
92 | 17 Mar 2026 | Tue | Technical - Testing & QA | Basic load testing | Simulate 50-100 concurrent users. Identify bottlenecks. Booking under load | RCB | MEDIUM | Not Started
93 | 17 Mar 2026 | Tue | Physio Recruitment | Physio platform walkthrough session | Video call / webinar with all physios. Demo platform. Q&A. Gather feedback | SRH | HIGH | Not Started | Physios onboarded
94 | 18 Mar 2026 | Wed | Technical - Testing & QA | Fix all bugs from staging / cross-browser | Address every remaining issue. Regression test | RCB | CRITICAL | Not Started | Staging test
95 | 18 Mar 2026 | Wed | Technical - Infrastructure | Production deployment (soft launch) | Deploy to production. Verify all services. Monitor errors. Invite-only mode | RCB | CRITICAL | Not Started | All tests pass
96 | 18 Mar 2026 | Wed | Technical - Infrastructure | Set up uptime monitoring | UptimeRobot / Better Uptime. Monitor: site, API, DB, payments. Alerts | RCB | HIGH | Not Started | Prod deploy
97 | 18 Mar 2026 | Wed | Marketing & Pre-Launch | Schedule pre-launch social media (10 days) | Daily teaser content. Behind the scenes, physio spotlights, countdown | SRH | HIGH | Not Started | Social accounts
98 | 19 Mar 2026 | Thu | Technical - Payments | Verify live payment flow end-to-end | Real £1 test booking full flow. Verify physio payout. All emails sent correctly | RCB | CRITICAL | Not Started | Live Stripe
99 | 19 Mar 2026 | Thu | Marketing & Pre-Launch | Send email to waitlist — launch coming | Email all pre-registered users. Early-bird offer. Launch date reveal | SRH | HIGH | Not Started | Email mktg
100 | 19 Mar 2026 | Thu | Marketing & Pre-Launch | Prepare press release | Local press, health publications, physio trade press. Draft newsworthy angle | SRH | MEDIUM | Not Started
101 | 19 Mar 2026 | Thu | Operations & Support | Set up live chat widget | Tawk.to (free) or Crisp. Key pages: booking, contact, physio sign-up | RCB | MEDIUM | Not Started
102 | 20 Mar 2026 | Fri | Technical - Testing & QA | Beta test with 5-10 friendly users | Real users make real test bookings. Feedback on UX, flow, clarity, trust | RCB | CRITICAL | Not Started | Soft launch
103 | 20 Mar 2026 | Fri | Physio Recruitment | Confirm all physios ready for launch | Final check: profiles ✓, availability ✓, insurance ✓, HCPC ✓, payout ✓ | SRH | CRITICAL | Not Started
104 | 21 Mar 2026 | Sat | Technical - Testing & QA | Fix critical issues from beta feedback | Showstopper bugs or UX issues. Fast turnaround fixes | RCB | CRITICAL | Not Started | Beta test
105 | 21 Mar 2026 | Sat | Marketing & Pre-Launch | Pre-launch social media campaign kicks off | Daily countdown posts. Physio spotlights. Beta testimonials | SRH | HIGH | Not Started | Content ready
106 | 22 Mar 2026 | Sun | Technical - Testing & QA | Round 2 — re-test all fixed issues | Verify every beta fix. Full regression on critical paths | RCB | HIGH | Not Started | Beta fixes
107 | 22 Mar 2026 | Sun | Content & Copywriting | Write launch-week email sequence | Day-of launch, day+1 follow-up, day+3 reminder, day+7 re-engage | SRH | HIGH | Not Started
108 | 23 Mar 2026 | Mon | Legal & Company Formation | Final legal review — all policies & pages | Solicitor reviews T&Cs, Privacy, Physio Agreement. GDPR sign-off | SRH | CRITICAL | Not Started | All policies
109 | 23 Mar 2026 | Mon | Technical - Infrastructure | Final production deployment | Deploy final version. DB migrations. Clear caches. Verify integrations | RCB | CRITICAL | Not Started | All fixes
110 | 23 Mar 2026 | Mon | Technical - Testing & QA | Smoke test production | Quick test critical paths on live: sign up, search, book, pay, confirm | RCB | CRITICAL | Not Started | Final deploy
111 | 24 Mar 2026 | Tue | Operations & Support | Brief support process / prepare for launch | FAQ responses, common issue resolutions, escalation contacts, shift rota | SRH | HIGH | Not Started
112 | 24 Mar 2026 | Tue | Marketing & Pre-Launch | Send press release to media contacts | Local press, health publications, physio outlets. Follow up with key journos | SRH | MEDIUM | Not Started | Press release
113 | 24 Mar 2026 | Tue | Marketing & Pre-Launch | Prepare launch-day social media content | Announcement posts all platforms. Physio spotlight threads. Special offers | SRH | HIGH | Not Started
114 | 24 Mar 2026 | Tue | Technical - Infrastructure | Performance & stress test production | Final load test on prod. Verify auto-scaling. Check response times under load | RCB | HIGH | Not Started
115 | 25 Mar 2026 | Wed | Technical - Testing & QA | Final bug fixes & polish | Last-minute fixes. UI polish. Copy corrections. Final QA pass | RCB | CRITICAL | Not Started
116 | 25 Mar 2026 | Wed | Legal & Company Formation | Ensure all legal pages live on website | T&Cs, Privacy, Cookie Policy, Complaints — all linked in footer and working | SRH | CRITICAL | Not Started | Legal review
117 | 26 Mar 2026 | Thu | Technical - Infrastructure | Pre-launch checklist completion | SSL ✓, backups ✓, monitoring ✓, Sentry ✓, Stripe live ✓, emails ✓, all pages ✓ | RCB | CRITICAL | Not Started
118 | 26 Mar 2026 | Thu | Technical - Infrastructure | Scale infrastructure if needed | Check Vercel plan, Supabase limits, Stripe limits, email limits. Upgrade if needed | RCB | HIGH | Not Started
119 | 26 Mar 2026 | Thu | Operations & Support | Notify all physios — launch in 4 days | Personal message to each. Confirm launch-week availability. Build excitement | SRH | HIGH | Not Started
120 | 27 Mar 2026 | Fri | Marketing & Pre-Launch | Schedule all launch-day posts & emails | Pre-schedule social posts for 30 March. Email blast ready. Ads ready to activate | SRH | HIGH | Not Started
121 | 27 Mar 2026 | Fri | Technical - Testing & QA | Final smoke test — everything green | Last check: all critical paths, payments, emails, monitoring. Sign-off from RCB | RCB | CRITICAL | Not Started
122 | 28 Mar 2026 | Sat | Operations & Support | Dry run — simulate launch day operations | Run through launch-day checklist. Test support flow. Test monitoring alerts | SRH | HIGH | Not Started
123 | 28 Mar 2026 | Sat | Marketing & Pre-Launch | Final countdown posts — 2 days to go | Excitement building. Behind-the-scenes. Physio quotes. Launch teaser | SRH | HIGH | Not Started
124 | 29 Mar 2026 | Sun | Operations & Support | Final call with all physios — launch tomorrow | Last sync. Confirm everyone is ready. Share launch-day timeline | SRH | HIGH | Not Started
125 | 29 Mar 2026 | Sun | Technical - Infrastructure | Final system health check | All services green. Backups ran. Monitoring active. On-call schedule confirmed | RCB | CRITICAL | Not Started
126 | 30 Mar 2026 | Mon | Launch Day | 🚀 LAUNCH — Remove invite-only mode, GO LIVE | Open platform to public. Flip the switch. Remove beta flags. THIS IS IT! | RCB | CRITICAL | Not Started | All pre-launch
127 | 30 Mar 2026 | Mon | Launch Day | Monitor systems closely (ALL DAY) | Error rates, server load, payments, email delivery. Hotfix ready. RCB on-call | RCB | CRITICAL | Not Started | Launch
128 | 30 Mar 2026 | Mon | Launch Day | Publish launch social media posts — all platforms | LinkedIn, Instagram, Facebook, Twitter/X. Engage with comments all day | SRH | CRITICAL | Not Started | Launch
129 | 30 Mar 2026 | Mon | Launch Day | Send launch email to full mailing list | Launch announcement + offer/promotion. Clear CTA: book your first appointment | SRH | CRITICAL | Not Started | Launch
130 | 30 Mar 2026 | Mon | Launch Day | Activate Google Ads campaign | Turn on PPC: '[city] home physio', 'physio home visit near me' | SRH | HIGH | Not Started | Ads setup
131 | 30 Mar 2026 | Mon | Launch Day | Monitor first real bookings personally | Ensure first bookings go smoothly. Call physio & patient. Be on standby | SRH | CRITICAL | Not Started | Launch
132 | 30 Mar 2026 | Mon | Launch Day | Respond to ALL enquiries same day | Fast response critical. Support email, live chat, social DMs. SRH handles all | SRH | CRITICAL | Not Started | Launch
133 | 31 Mar 2026 | Tue | Post-Launch (Week 1) | Review Day 1 metrics & fix issues | Sign-ups, bookings, revenue, errors, feedback. Hotfix any critical bugs | RCB | CRITICAL | Not Started | Launch done
134 | 31 Mar 2026 | Tue | Post-Launch (Week 1) | Day 1 ops review — what worked, what broke | SRH reviews: support volume, physio feedback, patient complaints, booking flow | SRH | CRITICAL | Not Started | Launch done
135 | 01 Apr 2026 | Wed | Post-Launch (Week 1) | Gather feedback from first patients & physios | Call/message first users. NPS score. What worked? Pain points? Quick wins | SRH | HIGH | Not Started
136 | 01 Apr 2026 | Wed | Post-Launch (Week 1) | Iterate — quick-win UX fixes | Copy changes, flow improvements, UI tweaks based on real user behaviour | RCB | HIGH | Not Started | Feedback
137 | 02 Apr 2026 | Thu | Post-Launch (Week 1) | Continue physio recruitment — expand areas | Target: 25-30 physios month 1. Start recruiting in adjacent postcodes | SRH | HIGH | Not Started
138 | 02 Apr 2026 | Thu | Post-Launch (Week 1) | Run first Google Ads optimisation | Review ad performance, pause low performers, optimise bids, negative keywords | SRH | HIGH | Not Started | Ads running
139 | 03 Apr 2026 | Fri | Post-Launch (Week 1) | Verify first physio payout cycle | Confirm Stripe payouts reaching physios. Resolve any payment issues ASAP | RCB | CRITICAL | Not Started
140 | 03 Apr 2026 | Fri | Post-Launch (Week 1) | Set up weekly metrics dashboard | GMV, bookings/week, new users, new physios, retention, NPS, commission revenue | RCB | HIGH | Not Started
141 | 05 Apr 2026 | Sun | Post-Launch (Week 1) | Week 1 review & retrospective | Full review with SRH + RCB. What went well. What to improve. Month 1 goals | SRH | HIGH | Not Started
142 | 06 Apr 2026 | Mon | Post-Launch (Week 2-4) | Build recurring / follow-up booking feature | Patients book weekly sessions. Package discounts. Auto-rebook | RCB | HIGH | Not Started
143 | 06 Apr 2026 | Mon | Post-Launch (Week 2-4) | Launch referral programme | Patient refers friend → both get £10 off. Physio referral bonus. Track referrals | SRH | HIGH | Not Started
144 | 08 Apr 2026 | Wed | Post-Launch (Week 2-4) | Expand to 2nd geographic area | Based on demand data. Recruit physios in new area. Local marketing push | SRH | HIGH | Not Started
145 | 08 Apr 2026 | Wed | Post-Launch (Week 2-4) | Build automated review-request emails | 24hr post-appointment → request review. Follow up day 3 if no review | RCB | MEDIUM | Not Started
146 | 10 Apr 2026 | Fri | Post-Launch (Week 2-4) | Establish GP surgery partnerships | Leaflets in waiting rooms. Referral pathway from GPs. Outreach to local practices | SRH | HIGH | Not Started
147 | 10 Apr 2026 | Fri | Post-Launch (Week 2-4) | Build physio earnings & tax report | Monthly/annual earnings summary. CSV download. Help with self-assessment | RCB | HIGH | Not Started
148 | 13 Apr 2026 | Mon | Post-Launch (Week 2-4) | Content marketing — launch weekly blog | SEO: 'exercises for back pain', 'when to see a physio'. Weekly cadence | SRH | MEDIUM | Not Started
149 | 13 Apr 2026 | Mon | Post-Launch (Week 2-4) | Build advanced search filters | Specialisation, gender, language, price range, availability, rating filters | RCB | HIGH | Not Started
150 | 15 Apr 2026 | Wed | Post-Launch (Week 2-4) | Run first Facebook / Instagram ad campaign | Target: local area, 25-65, health-interested. A/B test creatives | SRH | HIGH | Not Started
151 | 15 Apr 2026 | Wed | Post-Launch (Week 2-4) | Build patient medical notes (physio-side) | Secure clinical notes per patient. Treatment plans. SOAP notes. GDPR storage | RCB | HIGH | Not Started
152 | 17 Apr 2026 | Fri | Post-Launch (Week 2-4) | Research NHS referral pathway integration | Can GPs refer via platform? NHS Choose & Book. Private + NHS hybrid? | SRH | MEDIUM | Not Started
153 | 17 Apr 2026 | Fri | Post-Launch (Week 2-4) | Implement push notifications (web) | Browser push: new bookings (physio), confirms (patient), reminders | RCB | MEDIUM | Not Started
154 | 20 Apr 2026 | Mon | Post-Launch (Week 2-4) | Month 1 board review / investor update | Metrics: users, bookings, revenue, growth, unit economics. Plan Month 2 | SRH | HIGH | Not Started
155 | 20 Apr 2026 | Mon | Post-Launch (Week 2-4) | Apply for startup grants / funding (if needed) | Innovate UK, SEIS/EIS angels, Seedrs/Crowdcube. Start Fund, Tech Nation | SRH | MEDIUM | Not Started
156 | 22 Apr 2026 | Wed | Post-Launch (Week 2-4) | File first VAT return (if applicable) | If approaching £90k threshold. Register. MTD-compliant software | SRH | MEDIUM | Not Started
157 | 22 Apr 2026 | Wed | Post-Launch (Week 2-4) | Hire first customer support person (part-time) | Handle growing enquiries. Train on playbook. Cover evenings/weekends | SRH | MEDIUM | Not Started
158 | 27 Apr 2026 | Mon | Post-Launch (Month 2) | Begin mobile app development (React Native) | Native patient app. Push notifs, location, quick rebook. MVP scope | RCB | HIGH | Not Started
159 | 27 Apr 2026 | Mon | Post-Launch (Month 2) | Automate DBS check verification | Provider integration (uCheck / DBS Online). Reduce manual verification | RCB | HIGH | Not Started
160 | 01 May 2026 | Fri | Post-Launch (Month 2) | Build physio mobile app / PWA | Physios need mobile: bookings, directions, availability on-the-go | RCB | HIGH | Not Started
161 | 01 May 2026 | Fri | Post-Launch (Month 2) | Launch corporate wellness partnerships | Approach companies for employee physio benefits. B2B pricing. Corp accounts | SRH | HIGH | Not Started
162 | 04 May 2026 | Mon | Post-Launch (Month 2) | Implement insurance claim assistance | Help patients claim on private insurance (Bupa, AXA, Vitality). Receipt gen | RCB | HIGH | Not Started
163 | 04 May 2026 | Mon | Post-Launch (Month 2) | Expand to 3rd & 4th geographic areas | Data-driven expansion. Recruit physios. Localised marketing per area | SRH | HIGH | Not Started
164 | 08 May 2026 | Fri | Post-Launch (Month 2) | Build appointment reminder automation | SMS + email: 24hr + 2hr before. Reduce no-shows by 40%+ | RCB | HIGH | Not Started
165 | 08 May 2026 | Fri | Post-Launch (Month 2) | Set up physio ambassador programme | Top physios as ambassadors. Recruit other physios for bonus. Brand advocates | SRH | MEDIUM | Not Started
166 | 11 May 2026 | Mon | Post-Launch (Month 2) | Implement physio performance scoring | Internal score: reviews, on-time rate, completion rate, retention | RCB | MEDIUM | Not Started
167 | 11 May 2026 | Mon | Post-Launch (Month 2) | Hire operations assistant (part-time) | Physio vetting, customer Qs, day-to-day ops. Free up founder time | SRH | MEDIUM | Not Started
168 | 15 May 2026 | Fri | Post-Launch (Month 2) | First quarterly compliance audit | GDPR data audit, HCPC compliance, insurance renewals, policy review | SRH | HIGH | Not Started
169 | 18 May 2026 | Mon | Post-Launch (Month 2) | Month 2 review & growth planning | Full metrics. Growth rate, retention, LTV, CAC. Set Month 3 targets | SRH | HIGH | Not Started
170 | 25 May 2026 | Mon | Post-Launch (Month 3+) | Launch patient mobile app (App Store + Play Store) | Submit Apple + Google. ASO. Launch marketing campaign for app | RCB | HIGH | Not Started | App dev done
171 | 25 May 2026 | Mon | Post-Launch (Month 3+) | Explore seed / Series fundraising | Pitch deck, financial model, investor outreach. Target £250k-500k seed | SRH | HIGH | Not Started | Month 2 metrics
172 | 01 Jun 2026 | Mon | Post-Launch (Month 3+) | Implement video consultation feature | Pre-assessment video calls. Follow-up consults. Expand beyond home visits | RCB | MEDIUM | Not Started
173 | 01 Jun 2026 | Mon | Post-Launch (Month 3+) | National expansion planning | Roadmap: top 10 UK cities. Recruitment pipeline. Marketing per city | SRH | HIGH | Not Started
174 | 08 Jun 2026 | Mon | Post-Launch (Month 3+) | Build multi-language support | English, Polish, Hindi, Bengali, Urdu (UK demographics). i18n framework | RCB | MEDIUM | Not Started
175 | 08 Jun 2026 | Mon | Post-Launch (Month 3+) | Establish Advisory Board (clinical governance) | Senior physio, healthcare lawyer, NHS advisor, tech advisor. Quarterly meets | SRH | HIGH | Not Started
176 | 15 Jun 2026 | Mon | Post-Launch (Month 3+) | Implement AI-powered physio matching | Match by condition, location, specialisation, reviews, price, availability | RCB | MEDIUM | Not Started
177 | 15 Jun 2026 | Mon | Post-Launch (Month 3+) | Launch loyalty / subscription programme | Monthly sub: 2 sessions at discount. Annual & family plans | SRH | HIGH | Not Started
178 | 22 Jun 2026 | Mon | Post-Launch (Month 3+) | Build API for clinic / hospital integrations | Clinics refer patients, check availability, track outcomes. B2B growth | RCB | MEDIUM | Not Started
179 | 22 Jun 2026 | Mon | Post-Launch (Month 3+) | CQC registration assessment (if applicable) | Care Quality Commission. Assess requirements. Begin registration if needed | SRH | HIGH | Not Started
180 | 30 Jun 2026 | Tue | Post-Launch (Month 3+) | Quarter 1 full business review | Revenue, growth, burn, metrics, NPS, competition. Set Q2 OKRs | SRH | HIGH | Not Started

## Team Ownership
TEAM OWNERSHIP — SRH (UK, Operations) vs RCB (Bangalore, Technical)
Team | Location | Tasks | % Share | Scope
🔵 SRH | United Kingdom 🇬🇧 | 91 | 51% | Legal, Compliance, Insurance, Finance, Recruitment, Marketing, Content, Operations, Support, Physio Onboarding
🟣 RCB | Bangalore, India 🇮🇳 | 89 | 49% | Infrastructure, Backend, Frontend, Payments, Testing/QA, Design, DevOps, Security, Monitoring, Mobile App
TOTAL |  | 180 | 100%
💰 PAYMENT SCHEDULE: SRH → RCB
Date | Instalment | Amount (₹) | Cumulative (₹) | Status
4 March 2026 (Wed) | 1st Instalment | ₹50,000 | ₹50,000 | Pending
5 March 2026 (Thu) | 2nd Instalment | ₹50,000 | ₹1,00,000 | Pending
6 March 2026 (Fri) | 3rd & FINAL Instalment | ₹50,000 | ₹1,50,000 ✅ | Pending
| TOTAL | ₹1,50,000
Notes:
• SRH pays RCB ₹1,50,000 total within first 3 days (4-6 March). 3 × ₹50,000 instalments.
• Payment via bank transfer / UPI. Collect receipt for each instalment.
• Covers RCB's full platform build through launch (30 March).
• Post-launch technical work (Month 2+) to be agreed as separate engagement.
• RCB technical work begins Day 1 but first payment is on Day 3 (good faith start).
📋 SRH — Tasks by Category
Category | Tasks
Marketing & Pre-Launch | 13
Legal & Company Formation | 12
Post-Launch (Week 2-4) | 10
Physio Recruitment | 9
Operations & Support | 7
Content & Copywriting | 6
Post-Launch (Month 2) | 6
Post-Launch (Month 3+) | 6
Launch Day | 5
Post-Launch (Week 1) | 5
Regulatory & Compliance | 4
Insurance | 3
💰 Payment: SRH → RCB | 3
Finance & Banking | 1
Technical - Payments | 1
📋 RCB — Tasks by Category
Category | Tasks
Technical - Backend | 19
Technical - Infrastructure | 15
Technical - Testing & QA | 15
Technical - Frontend | 9
Post-Launch (Week 2-4) | 6
Post-Launch (Month 2) | 6
Post-Launch (Month 3+) | 5
Post-Launch (Week 1) | 4
Technical - Payments | 3
Design & Branding | 2
Marketing & Pre-Launch | 2
Launch Day | 2
Operations & Support | 1

## Gantt Overview
GANTT OVERVIEW — 2 March → 30 March 2026 (28 days to launch)
Category | Owner | 02 Mon | 03 Tue | 04 Wed | 05 Thu | 06 Fri | 07 Sat | 08 Sun | 09 Mon | 10 Tue | 11 Wed | 12 Thu | 13 Fri | 14 Sat | 15 Sun | 16 Mon | 17 Tue | 18 Wed | 19 Thu | 20 Fri | 21 Sat | 22 Sun | 23 Mon | 24 Tue | 25 Wed | 26 Thu | 27 Fri | 28 Sat | 29 Sun | 30 Mon
Legal & Company Formation | SRH
Regulatory & Compliance | SRH
Finance & Banking | SRH
💰 Payment: SRH → RCB | SRH
Insurance | SRH
Design & Branding | RCB
Technical - Infrastructure | RCB
Technical - Backend | RCB
Technical - Frontend | RCB
Technical - Payments | RCB
Technical - Testing & QA | RCB
Content & Copywriting | SRH
Physio Recruitment | SRH
Marketing & Pre-Launch | SRH
Operations & Support | SRH
Launch Day | SRH

## Budget Estimate
BUDGET ESTIMATE
Category | Item | Cost (£) | Frequency | Paid By | Notes
💰 RCB Payment | Technical dev fee (₹1,50,000) | 1450 | One-off | SRH | ₹1.5L ≈ ~£1,450. 3 instalments 4-6 Mar
Company | Companies House registration | 12 | One-off | SRH
Company | Registered office address | 50 | Annual | SRH | Virtual office if needed
Legal | Solicitor review (T&Cs, Privacy) | 500 | One-off | SRH | Template + review £300-700
Legal | ICO registration | 40 | Annual | SRH | Required by law
Domains | Domain (.co.uk + .com) | 20 | Annual | SRH
Hosting | Vercel Pro | 20 | Monthly | SRH | Free tier may suffice initially
Database | Supabase Pro | 25 | Monthly | SRH | Free tier to start
Payments | Stripe fees | 0 | Per txn | — | 1.4% + 20p per UK card
Email | SendGrid / Resend | 0 | Monthly | SRH | Free tier: 100/day
Email Mktg | Mailchimp / Brevo | 0 | Monthly | SRH | Free ≤500 contacts
Insurance | Public Liability | 300 | Annual | SRH | £200-500 range
Insurance | Professional Indemnity | 400 | Annual | SRH | £300-600 range
Design | Logo (Fiverr/99designs) | 100 | One-off | RCB | Expense or included in fee
Marketing | Google Ads (month 1) | 500 | Monthly | SRH | £15-20/day
Marketing | Social media ads | 300 | Monthly | SRH | Facebook / Instagram
Monitoring | Sentry | 0 | Monthly | RCB | Free tier
Monitoring | UptimeRobot | 0 | Monthly | RCB | Free tier
Support | Tawk.to live chat | 0 | Monthly | SRH | Free
SMS | Twilio (optional) | 50 | Monthly | SRH | ~3p per SMS
Misc | Contingency buffer | 200 | One-off | SRH
| ESTIMATED TOTAL | 3967

## Key Resources
KEY RESOURCES & LINKS
Category | Resource | URL | Notes
Legal | Companies House | companieshouse.gov.uk | Registration
Legal | ICO | ico.org.uk | Data protection
Legal | HMRC | gov.uk/register-for-self-assessment | Tax
Regulatory | HCPC Register | hcpc-uk.org/check-the-register/ | Verify physios
Regulatory | CSP | csp.org.uk | Chartered Society
Banking | Tide | tide.co | Fast business banking
Insurance | Hiscox | hiscox.co.uk | Business insurance
Insurance | Simply Business | simplybusiness.co.uk | Compare
Technical | Vercel | vercel.com | Hosting
Technical | Supabase | supabase.com | DB + Auth
Technical | Stripe Connect | stripe.com/connect | Payments
Technical | SendGrid | sendgrid.com | Email
Technical | Sentry | sentry.io | Error monitoring
Technical | postcodes.io | postcodes.io | UK postcode API
Marketing | Google Ads | ads.google.com | PPC
Marketing | Meta Business | business.facebook.com | Social ads
Marketing | Mailchimp | mailchimp.com | Email marketing
Recruitment | CSP Jobs | csp.org.uk/jobs | Physio jobs
Recruitment | Indeed UK | indeed.co.uk | Jobs
Recruitment | LinkedIn | linkedin.com | Professional
Funding | Innovate UK | innovateuk.ukri.org | Grants
Compliance | CQC | cqc.org.uk | Care Quality Commission

## Risk Register
RISK REGISTER
# | Risk | Impact | Likelihood | Mitigation | Owner
1 | Not enough physios at launch | HIGH | MEDIUM | Recruit early. 10-15 min. Focus 1-2 areas. Direct outreach | SRH
2 | Stripe Connect approval delayed | HIGH | LOW | Apply Day 5. Manual invoicing backup. Chase Stripe support | SRH
3 | HCPC verification issues | HIGH | LOW | Manual backup. Cross-ref HCPC online register directly | RCB
4 | Low patient demand at launch | MEDIUM | MEDIUM | Waitlist, Google Ads, social media, local press, GP leaflets | SRH
5 | Technical bugs on launch day | HIGH | MEDIUM | Extensive QA, staging env, Sentry. RCB on-call all day (IST evening) | RCB
6 | Legal / compliance gap | HIGH | LOW | Early solicitor review. HCPC, ICO, GDPR. Safeguarding policy | SRH
7 | Physio no-shows / poor quality | HIGH | LOW | Vetting, reviews, agreement standards. Suspension policy | SRH
8 | Payment disputes / chargebacks | MEDIUM | MEDIUM | Clear T&Cs, cancellation policy, Stripe Radar, dispute process | RCB
9 | Data breach / security incident | HIGH | LOW | HTTPS, encryption, RLS, backups, GDPR compliance, ICO plan | RCB
10 | RCB payment delayed by SRH | HIGH | LOW | Payment split 3 × ₹50k over days 3-5. Blocks dev if delayed | SRH
11 | Timezone friction (UK ↔ Bangalore) | MEDIUM | MEDIUM | Daily standup overlap (1-3pm UK / 6:30-8:30pm IST). Async Slack | SRH
12 | IR35 / contractor status risk | HIGH | LOW | Legal advice on IR35. HMRC CEST tool. Compliant contracts | SRH

## Launch Day Checklist
🚀 LAUNCH DAY — 30 MARCH 2026 (Monday)
RCB works IST (overlap with UK: 1:30pm-8:30pm IST = 8am-3pm UK) ¦ SRH works UK time
Time (UK) | Task | Owner | Done?
06:30 | Final system health check — all services green | RCB
07:00 | Verify Stripe live mode active | RCB
07:00 | Verify email delivery (send test) | RCB
07:30 | Remove invite-only / beta flags | RCB
07:30 | Verify site accessible at live domain | RCB
08:00 | Post launch announcement — LinkedIn | SRH
08:00 | Post launch announcement — Instagram | SRH
08:00 | Post launch announcement — Facebook | SRH
08:00 | Post launch announcement — Twitter/X | SRH
08:30 | Send launch email to mailing list | SRH
08:30 | Activate Google Ads campaigns | SRH
09:00 | Monitor first sign-ups and bookings | SRH
09:00 | Check Sentry error dashboard | RCB
10:00 | Verify all physios showing in search | SRH
10:00 | Test real booking flow on production | RCB
12:00 | Midday metrics: sign-ups, bookings, errors | SRH
12:00 | Respond to all support enquiries | SRH
14:00 | Post afternoon social media update | SRH
14:30 | Check payment processing (RCB overlap ends ~3pm UK) | RCB
17:00 | End of day metrics review | SRH
17:00 | Send thank-you to all physios | SRH
18:00 | Evening social media engagement | SRH
21:00 | Final system check (RCB morning IST) | RCB